## Tabelle1
| April |  |  |  |  | May |  |  |  |  | June |  |  |  | July |  |  |  |  | August |  |  |  |  | September
| 1-7 | 8-14 | 15-21 | 22-28 | 29-30 | 1-5 | 6-12 | 13-19 | 20-27 | 27-31 | 3-9 | 10-16 | 17-23 | 24-30 | 1-7 | 8-14 | 15-21 | 22-28 | 29-31 | 1-4 | 5-11 | 12-18 | 19-25 | 26-31 | 2-8 | 9-15 | 16-22 | 23-30
DETERMINATION OF INVERTER ROCOP
Simulation of scenarios with different RE penetration in DigSilent with IEEE 9 busbars model
Estimation of measuring, filtering and processing frequency signal
Implementation of IEEE 9 busbars in Simulink
Determination of ROCOP
Analysis of renewables response in Digsilent
SIMULATION IN GRID LAB
Getting to know the equipment (Manual, programming…)
Grid simulation and comparisson of results
POWER ELECTRONICS
State of the art in regards, time of reaction and power delivery
Identification of areas for improvement
(idealy) Propose a model
WRITING MASTER THESIS
First draft
Final Submition
Critical priority
Optional
Normal priority