## Tabelle1
| April |  |  |  |  | May |  |  |  |  | June |  |  |  | July |  |  |  |  | August |  |  |  |  | September
| 1-7 | 8-14 | 15-21 | 22-28 | 29-30 | 1-5 | 6-12 | 13-19 | 20-27 | 27-31 | 3-9 | 10-16 | 17-23 | 24-30 | 1-7 | 8-14 | 15-21 | 22-28 | 29-31 | 1-4 | 5-11 | 12-18 | 19-25 | 26-31 | 2-8 | 9-15 | 16-22 | 23-30
DETERMINATION OF INVERTER ROCOP
Simulation of scenarios with different RE penetration on IEEE 9 bus system
Investigation of measuring, filtering and processing frequency signal time
Power rate estimation to avoid frequency collapse
Analysis of renewables response as frequency support
SIMULATION IN GRID LAB
Getting to know the equipment (Specsheets)
Grid simulation and comparisson of results
POWER ELECTRONICS
State of the art in regards reaction time and power rate delivery
Identification of areas for improvement
WRITING MASTER THESIS
First draft Submission
Final Submission
Critical priority
Optional
No Critical